## Velocity
Sprint | Sprint Start Date | Sprint End Date | Comittment | Unplanned | Done | Done Percentage | Velocity AVG | Total Sprint SP | Carry Over SP | Carry Over Percetage | Capacity SP | Workday % | User Stories Done
Sprint 15 | 2026-07-15 | 2026-07-28 23:59 | 47 | 35 | 77 | 163.8% | 77 | 82 | 2 | 4.255% | 80 | 91.82%
Sprint 16 | 2026-07-29 | 2026-08-11 23:59 | 62 | 12 | 69 | 111.3% | 73 | 74 | 2 | 3.226% | 72 | 84.55%
Sprint 17 | 2026-08-12 | 2026-08-25 23:59 | 143 | 32 | 135 | 94.41% | 93.6667 | 162 | 18 | 12.59% | 144 | 87.27%
Sprint 18 | 2026-08-26 | 2026-09-08 23:59
Note on D26: sum of SP that were committed to the sprint.
Note on E26: Sum of SP that were added to the ongoing sprint (Production Support)
Note on F26: Sum of SP from fully done tickets according the DoD
Note on H26: Avarage speed considering Done SP per sprint
Note on I26: Total Story Points within the sprint including committed and adhered (Scope Creep)
Note on J26: Total SP that spill into the following sprint because were not finished. (If only testing is pending at least 2 SP are spilled)
Note on K26: Total CarryOver SP over Total committed
Note on L26: Gina Pardini: Total SP completed in a sprint.
Note on M26: Percentage of the workdays that were not Holidays or PTOs
Note on N26: How many Stories where done in the sprint

## Capacity
[6 empty] | Sprint 15 (Jul15-Jul28) |  |  |  |  | Sprint 16 (Jul29-Ago11) |  |  |  |  | Sprint 17 (Ago11-Ago25) | [5 empty] | Sprint 18 (Ago26-Sep8)
Working days | Capcity | Location | Developer/Admin | Capacity per day | Capacity per sprint | Holidays | PTO | Working Days | Completed | AVG SP15 | Holidays | PTO | Working Days | Completed | AVG SP16 | Holidays | PTO | Working Days | Committed | Completed | AVG SP17 | Holidays | PTO | Working Days | Capacity | Comitted | Completed | AVG SP18
10 | 100% | India | Apala Sen | 0.76111 | 7.6111 | 1 |  | 9 | 11 | 1.2222 |  |  | 10 | 3 | 0.3 |  |  | 10 | 16 | 19 |  | 1 |  | 9 | 12
10 | 100% | Argentina | Carlos Juarez | 0.8 | 8 |  |  | 10 | 8 | 0.8 |  |  | 10 | 8 | 0.8 | 1 | 3 | 6 | 5 | 13 |  |  |  | 10 | 8
10 | 100% | Colombia | Santiago Epalza | 0 | 0 | 1 |  | 9 | 0 | 0 | 1 |  | 9 | 0 | 0 | 1 |  | 9 | 5 | 8 |  |  | 1 | 9 | 8
10 | 100% | Argentina | Tomas Olivera | 0.26667 | 2.6667 |  | 1 | 9 | 3 | 0.33333 |  |  | 10 | 2 | 0.2 | 1 |  | 9 | 10 | 10 |  |  |  | 10 | 8
10 | 100% | India | Ataul Khalique | 0.41667 | 4.1667 | 1 |  | 9 | 3 | 0.33333 |  |  | 10 | 5 | 0.5 |  |  | 10 | 15 | 22 |  | 1 |  | 9 | 12
10 | 100% | Colmbia | Sebastian Perez | 0.96667 | 9.6667 | 1 |  | 9 | 3 | 0.33333 | 1 | 4 | 5 | 8 | 1.6 | 1 | 9 | 0 | 0 | 0 |  |  | 4 | 6 | 5
10 | 100% | India | Manish Raj | 1.3889 | 13.8889 | 1 |  | 9 | 16 | 1.7778 |  |  | 10 | 10 | 1 |  |  | 10 | 10 | 12 |  | 1 |  | 9 | 12
10 | 100% | India | Mahika Agrawal | 0.87222 | 8.7222 | 1 |  | 9 | 4 | 0.44444 |  |  | 10 | 13 | 1.3 |  |  | 10 | 14 | 12 |  | 1 |  | 9 | 12
10 | 100% | Colombia | Jacobo Salazar | 0.88889 | 8.8889 | 1 |  | 9 | 6 | 0.66667 | 1 |  | 9 | 10 | 1.1111 | 1 |  | 9 | 12 | 8 |  |  |  | 10 | 8
10 | 100% | Chile | Ignacio Toledo | 0.64444 | 6.4444 | 1 |  | 9 | 8 | 0.88889 |  |  | 10 | 4 | 0.4 |  |  | 10 | 20 | 22 |  |  |  | 10 | 12
10 | 50% | USA | Victor Cabrera | 0.4 | 4 |  |  | 10 | 8 | 0.8 |  |  | 10 | 0 | 0 |  |  | 10 | 12 | 12 |  | 1 | 4 | 5 | 8
Note on X31: Gina Pardini: Ago 31 - sep 4

## Holidays
Type | Date | Day | Impacts Work Calendar | Holiday | Comments | Country | ID
Holiday | 2026-01-01 | Thursday | Yes | New Year's Day |  | Chile | CL
Holiday | 2026-04-03 | Friday | Yes | Good Friday |  | Chile | CL
Holiday | 2026-04-04 | Saturday | No | Easter Saturday |  | Chile | CL
Holiday | 2026-05-01 | Friday | Yes | Labour Day |  | Chile | CL
Holiday | 2026-05-21 | Thursday | Yes | Glorias Navales day |  | Chile | CL
Holiday | 2026-06-21 | Sunday | No | National Day of the Indigenous Peoples |  | Chile | CL
Holiday | 2026-06-29 | Monday | Yes | Saint Peter and Saint Paul |  | Chile | CL
Holiday | 2026-07-16 | Thursday | Yes | Day of the Virgin of Carmen |  | Chile | CL
Holiday | 2026-08-15 | Saturday | No | Assumption of Mary |  | Chile | CL
Holiday | 2026-09-18 | Friday | Yes | Independence Day |  | Chile | CL
Holiday | 2026-09-19 | Saturday | No | Day of the Glories of the Army |  | Chile | CL
Holiday | 2026-10-12 | Monday | Yes | Meeting of Two Worlds |  | Chile | CL
Holiday | 2026-10-31 | Saturday | No | Day of the evangelical and protestant churches |  | Chile | CL
Holiday | 2026-11-01 | Sunday | No | All Saints' Day |  | Chile | CL
Holiday | 2026-12-08 | Tuesday | Yes | Day of the Immaculate Conception |  | Chile | CL
Holiday | 2026-12-25 | Friday | Yes | Christmas Day |  | Chile | CL
Holiday | 2026-01-01 | Thursday | Yes | New Year's Day |  | Colombia | CO
Holiday | 2026-01-12 | Monday | Yes | Epiphany |  | Colombia | CO
Holiday | 2026-03-23 | Monday | Yes | Saint Joseph's Day |  | Colombia | CO
Holiday | 2026-04-02 | Thursday | Yes | Maundy Thursday |  | Colombia | CO
Holiday | 2026-04-03 | Friday | Yes | Good Friday |  | Colombia | CO
Holiday | 2026-05-01 | Friday | Yes | Labour Day |  | Colombia | CO
Holiday | 2026-05-18 | Monday | Yes | Ascension Day |  | Colombia | CO
Holiday | 2026-06-08 | Monday | Yes | Corpus Christi |  | Colombia | CO
Holiday | 2026-06-15 | Monday | Yes | Sacred Heart of Jesus |  | Colombia | CO
Holiday | 2026-06-29 | Monday | Yes | Saint Peter and Saint Paul |  | Colombia | CO
Holiday | 2026-07-13 | Monday | Yes | Day of the Virgin of Chiquinquirá |  | Colombia | CO
Holiday | 2026-07-20 | Monday | Yes | Independence Day |  | Colombia | CO
Holiday | 2026-08-07 | Friday | Yes | Battle of Boyaca |  | Colombia | CO
Holiday | 2026-08-17 | Monday | Yes | Assumption of Mary |  | Colombia | CO
Holiday | 2026-10-12 | Monday | Yes | Colombus Day |  | Colombia | CO
Holiday | 2026-11-02 | Monday | Yes | All Saints' Day |  | Colombia | CO
Holiday | 2026-11-16 | Monday | Yes | Independence of Cartagena |  | Colombia | CO
Holiday | 2026-12-08 | Tuesday | Yes | Day of the Immaculate Conception |  | Colombia | CO
Holiday | 2026-12-25 | Friday | Yes | Christmas Day |  | Colombia | CO
Holiday | 2026-01-01 | Thursday | Yes | New year's day |  | Argentina | AR
Holiday | 2026-02-16 | Monday | Yes | Carnival |  | Argentina | AR
Holiday | 2026-02-17 | Tuesday | Yes | Carnival |  | Argentina | AR
Holiday | 2026-03-24 | Tuesday | Yes | National Day of Memory for Truth and Justice |  | Argentina | AR
Holiday | 2026-04-02 | Thursday | Yes | Day of the Veterans and Fallen of the Malvinas War |  | Argentina | AR
Holiday | 2026-04-03 | Friday | Yes | Good Friday |  | Argentina | AR
Holiday | 2026-05-01 | Friday | Yes | Labor Day |  | Argentina | AR
Holiday | 2026-05-25 | Monday | Yes | May Revolution |  | Argentina | AR
Holiday | 2026-06-15 | Monday | Yes | Martín Miguel de Güemes' Day |  | Argentina | AR
Holiday | 2026-06-20 | Saturday | No | Commemoration of the death of General Manuel Belgrano |  | Argentina | AR
Holiday | 2026-07-09 | Thursday | Yes | Independence Day |  | Argentina | AR
Regional Holiday | 2026-07-25 | Saturday | No | Holiday of Mendoza Province (depending on region) | Mendoza | Argentina | AR
Holiday | 2026-08-17 | Monday | Yes | Step to the Immortality of General José de San Martin |  | Argentina | AR
Holiday | 2026-10-12 | Monday | Yes | Day of Respect for Cultural Diversity |  | Argentina | AR
Holiday | 2026-11-23 | Monday | Yes | National Sovereignty Day |  | Argentina | AR
Holiday | 2026-12-08 | Tuesday | Yes | Immaculate Conception of Mary |  | Argentina | AR
Holiday | 2026-12-25 | Friday | Yes | Christmas Day |  | Argentina | AR
Holiday | 2026-01-01 | Thursday | Yes | New Year’s Day | All Entities | United States of America | US
Holiday | 2026-01-19 | Monday | Yes | Martin Luther King, Jr.´s Birthday | not EU51 | United States of America | US
Holiday | 2026-02-16 | Monday | Yes | President´s day | not EU51 | United States of America | US
Holiday | 2026-05-25 | Monday | Yes | Memorial Day | All Entities | United States of America | US
Holiday | 2026-06-19 | Friday | Yes | Juneteenth National Ind. Day | not EU51 | United States of America | US
Holiday | 2026-07-03 | Friday | Yes | Independence Day | All Entities | United States of America | US
Holiday | 2026-09-07 | Monday | Yes | Labor Day | All Entities | United States of America | US
Holiday | 2026-10-12 | Monday | Yes | Columbus Day | not EU51 | United States of America | US
Holiday | 2026-11-26 | Thursday | Yes | Thanksgiving Day | All Entities | United States of America | US
Holiday | 2026-11-27 | Friday | Yes | Day After Thanksgiving Day | not EU51 | United States of America | US
Holiday | 2026-12-25 | Friday | Yes | Christmas Day | All Entities | United States of America | US
Holidays | 2026-01-01 | Thursday | Yes | New Year´s Day | Mandatory | India | IN
Holidays | 2026-01-14 | Wednesday | Yes | Makar Sankranti | Optional | India | IN
Holidays | 2026-01-26 | Monday | Yes | Republic Day | Mandatory | India | IN
Holidays | 2026-03-03 | Tuesday | Yes | Dhulivandan | Optional | India | IN
Holidays | 2026-03-19 | Thursday | Yes | Gudhipadwa | Optional | India | IN
Holidays | 2026-03-31 | Tuesday | Yes | Mahavir Jayanti | Optional | India | IN
Holidays | 2026-04-03 | Friday | Yes | Good Friday | Optional | India | IN
Holidays | 2026-04-14 | Tuesday | Yes | Ambedkar Jayanti | Optional | India | IN
Holidays | 2026-05-01 | Friday | Yes | Labour Day | Mandatory | India | IN
Holidays | 2026-05-27 | Wednesday | Yes | Bakari Eid | Optional | India | IN
Holidays | 2026-06-02 | Tuesday | Yes | Telangana State Formation Day | Mandatory (Only for Hyderabad) | India | IN
Holidays | 2026-07-16 | Thursday | Yes | Rath Yatra | Optional | India | IN
Holidays | 2026-08-28 | Friday | Yes | Raksha Bandhan | Optional | India | IN
Holidays | 2026-09-14 | Monday | Yes | Ganesh Chaturthi | Mandatory | India | IN
Holidays | 2026-09-25 | Friday | Yes | Ganesh Visarjan | Optional | India | IN
Holidays | 2026-10-02 | Friday | Yes | Gandhi Jayanti | Mandatory | India | IN
Holidays | 2026-10-20 | Tuesday | Yes | Dussehra | Optional | India | IN
Holidays | 2026-11-06 | Friday | Yes | Diwali (Dhanteras) | Optional | India | IN
Holidays | 2026-12-25 | Friday | Yes | Christmas | Mandatory | India | IN
Holiday | 2026-01-01 | Thursday | Yes | New Year's Day |  | Mexico | MX
Holiday | 2026-02-02 | Monday | Yes | Constitution Day |  | Mexico | MX
Holiday | 2026-03-16 | Monday | Yes | Benito Juarez Birth Day |  | Mexico | MX
Holiday | 2026-04-02 | Thursday | Yes | Maundy Thursday |  | Mexico | MX
Holiday | 2026-04-03 | Friday | Yes | Good Friday |  | Mexico | MX
Holiday | 2026-05-01 | Friday | Yes | Labor Day |  | Mexico | MX
Holiday | 2026-05-10 | Sunday | No | Mother's Day |  | Mexico | MX
Holiday | 2026-09-16 | Wednesday | Yes | Independece Day |  | Mexico | MX
Holiday | 2026-11-02 | Monday | Yes | Death Day |  | Mexico | MX
Holiday | 2026-11-16 | Monday | Yes | Mexican Revolution Day |  | Mexico | MX
Holiday | 2026-12-25 | Friday | Yes | Christmas Day |  | Mexico | MX

## Sprint 15 Jul15-Jul28
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points (Estimated) | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation | Commited | Scope Creep Amount | Done
704283 | Story | Validation: SCTASK0374791 ¦ Legal/Compliance Request for Bulk PDF Generation of DSR Emails by Dealer and Date Range | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done |  | 2025-06-05 14:03 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | False | 3 |  | 3
735761 | Story | Spike: Investigate End-to-End Tracking for Platform Events | Sebastian Perez <conlbqr@jmfamily.com> | Sebastian Perez <conlbqr@jmfamily.com> | Done |  | 2025-07-23 11:57 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | False | 5 |  | 5
881577 | Story | [Tech Debt] Spike - Failed Flow Interviews ( 1 of 3 ) | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done |  | 2026-02-10 21:42 | 1 |  | 2026-07-15 | 2026-07-28 23:59 | False | 1 |  | 1
931784 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dynatrace | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-04-15 12:14 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | False | 5 |  | 5
933951 | Story | [Low] [Vulnerability Fix] Spike - Public static resources may expose data | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done |  | 2026-04-17 05:40 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | False | 5 |  | 5
944354 | Story | 07/15/2026 ¦ PROD Deployment ¦ SF Platform- DigitSec and Incidents | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin; carry-over 26.14; ProdDeploy | 2026-04-30 15:33 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | False | 5 |  | 5
957732 | Story | Spike: Salesforce Edge Network Mandatory Enablement Assessment (2026) | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; carry-over 26.12; carry-over 26.13; carry-over 26.14 | 2026-05-20 16:50 | 2 | 1 | 2026-07-15 | 2026-07-28 23:59 | False | 2
960470 | Story | [High*] [Vulnerability Fix] Cross Site Scripting in file pages/JMA_Reports_ACCT.page | Apala Sen <conjzwj@jmfamily.com> | Josh Wood <conadie@jmfamily.com> | Done | carry-over 26.13; carry-over 26.14; Dev; HIGH | 2026-05-26 16:56 | 3 | 0 | 2026-07-15 | 2026-07-28 23:59 | False | 3 |  | 3
971930 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.15 | N/A |  | Done |  | 2026-06-11 14:33 | 0 |  | 2026-07-15 | 2026-07-28 23:59 | False | 0 |  | 0
976504 | Story | Phishing - Resistant MFA Enforcement for Privileged Users (Implementation) | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | carry-over 26.13; carry-over 26.14; Dev | 2026-06-17 14:14 | 3 | 1 | 2026-07-15 | 2026-07-28 23:59 | False | 3
977929 | Story | [Zoom] - Key rotation to maintain seamless integration with SalesForce Lightning (UAT) | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-06-18 09:56 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | False | 5 |  | 5
985324 | Story | Initial DevOps Setup: GitHub Org Configuration, IdP Mapping, and Salesforce Prod Integration - Version 2 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done |  | 2026-06-29 12:09 | 8 |  | 2026-07-15 | 2026-07-28 23:59 | False | 8 |  | 8
991692 | Story | Commvault Phase 1 - Verify the Settings for Salesforce Production Integration for Commvault Backup (UAT/PROD) | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-07 08:19 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | False | 2 |  | 2
1003096 | Story | MIAW - Hypercare support | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Done |  | 2026-07-15 10:14 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
1004474 | Story | Setting up Custom URL for DealerSource 2.0 in UAT | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-16 07:31 | 1 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 1 | 1
1005118 | Story | Per asm RHT side of Dealer Portal is inoperative at this time | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Done |  | 2026-07-16 13:42 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 2 | 2
1005609 | Story | Production - MIAW User Stories: | N/A | felipe gonzalez <confjhw@jmfamily.com> | Done |  | 2026-07-17 08:10 | 0 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 0 | 0
1006303 | Story | UAT Deployments - Sprint 26.15 | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-20 02:58 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
1006800 | Story | Asbury Portal System Admins cannot Add Users | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done |  | 2026-07-20 14:26 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 2 | 2
1007131 | Story | Road ready hub receiving chats after hours | Mahika Agrawal <conjkak@jmfamily.com> | felipe gonzalez <confjhw@jmfamily.com> | Done |  | 2026-07-21 08:34 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
1008018 | Story | ACR AccountShare - Record Insert Failed; Manual Action Needed | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-22 06:22 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 2 | 2
1008170 | Story | 07/22/2026 ¦ ECHANGE ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done |  | 2026-07-22 09:11 | 5 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 5 | 5
1008266 | Bug | Cases removed from queue immediately upon assignment | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done |  | 2026-07-22 10:03 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
1009480 | Story | [Dynatrace App Synthetics] - Http monitor local outage for HTTP monitor JMA - Salesforce - IPs Check | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-07-23 11:59 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 2 | 2
1009553 | Story | Speech Analytics Integration - Track Case Fields in OCS Process | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Done |  | 2026-07-23 13:15 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
1010142 | Story | IT to IT request: Please assign to the appropriate group. | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-07-24 10:44 | 1 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 1 | 1
1010858 | Story | IT to IT request: Please assign to the appropriate group. | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-27 01:42 | 2 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 2 | 2
1010978 | Bug | Download statements issue still persist in Dealer Source | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Done |  | 2026-07-27 08:29 | 3 |  | 2026-07-15 | 2026-07-28 23:59 | True |  | 3 | 3
Note on J9: Gina Pardini: this was a carry over in 0 points. it was pending testing on Josh Wood.
Note on I10: Gina Pardini: 13 points not to be considered in metrics

## Sprint 16 Jul29-Ago11
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points (Estimated) | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation |  |  | Done
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation | Commited | Scope Creep Amount
761286 | Story | SCTASK0389150 - DPM Contact Create Access Automation | N/A | felipe gonzalez <confjhw@jmfamily.com> | Done | Carry Over Last Sprint (COLS) | 2025-08-20 10:25 | 3 |  | 2026-07-29 | 2026-08-11 23:59 | False | 3 |  | 3
820263 | Story | Flosum Summer 26 Release Analysis | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin; Dev | 2025-11-11 12:15 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | False | 5 |  | 5
906039 | Story | Restrict DealerSource Tabs and Features for Independent Repair Facility Permission Group | Habib Hasbun <jmasgeo@jmfamily.com> | Habib Hasbun <jmasgeo@jmfamily.com> | Done | Admin; Blocked | 2026-03-13 00:23 | 3 |  | 2026-07-29 | 2026-08-11 23:59 | False | 3 |  | 3
931780 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Mulesoft Integration | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Admin; INFO | 2026-04-15 12:07 | 8 |  | 2026-07-29 | 2026-08-11 23:59 | False | 8 |  | 8
932496 | Story | [Tech Debt] [Critical] [Vulnerability Fix] Custom Code Exposed on the Internet in file Saleforce Objects |  |  | Done | CRITICAL | 2026-04-16 07:53 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | False | 5 |  | 5
965965 | Story | 07/29/2026 ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; carry-over 26.15; ProdDeploy | 2026-06-02 16:20 | 5 | 2 | 2026-07-29 | 2026-08-11 23:59 | False | 5
982967 | Story | [Tech Debt] Fix JMA Seminar Process Flow Status Transition Logic | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Admin; carry-over 26.14; carry-over 26.15 | 2026-06-24 16:45 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | False | 5 |  | 5
984594 | Story | [Spike] Analyze SellingRelationship Date Synchronization Logic Between Salesforce Platform Events and Salesforce Backup View | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Dev; RELEVANT | 2026-06-26 11:36 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | False | 5 |  | 5
1001693 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.16 | N/A |  | Done | Admin; Dev | 2026-07-14 17:23 | 0 |  | 2026-07-29 | 2026-08-11 23:59 | False | 0 |  | 0
1001695 | Story | 08/05/2026 ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; ProdDeploy | 2026-07-14 17:26 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | False | 5 |  | 5
1007382 | Bug | Dealer Source ¦ Submit Claim menu is incorrectly displayed - Only UAT | N/A | julieth barrera <conqhvn@jmfamily.com> | Done | OnlyUAT | 2026-07-21 12:35 |  |  | 2026-07-29 | 2026-08-11 23:59 | False | 0 |  | 0
1009575 | Story | Speech Analytics Integration - Research Audit Report Logging for CallMiner Integration Access | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Done | Dev | 2026-07-23 13:44 | 2 |  | 2026-07-29 | 2026-08-11 23:59 | False | 2 |  | 2
1009998 | Story | Q3 - Phase 1 ¦ Business Scope SF Release ¦ Test Case Design | N/A | felipe gonzalez <confjhw@jmfamily.com> | Done |  | 2026-07-24 08:23 | 0 |  | 2026-07-29 | 2026-08-11 23:59 | False | 0 |  | 0
1011379 | Story | GitHub Release Enablement - Unit Test Remediation - Dealer Source | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Done | Dev | 2026-07-27 14:31 | 8 |  | 2026-07-29 | 2026-08-11 23:59 | False | 8 |  | 8
1011645 | Story | Account canonicals - AffiliationTerritoryCode, AffiliationRegionCore, and AffiliationManagerName not updating | Sebastian Perez <conlbqr@jmfamily.com> | Sebastian Perez <conlbqr@jmfamily.com> | Done | RELEVANT | 2026-07-27 16:29 | 8 |  | 2026-07-29 | 2026-08-11 23:59 | False | 8 |  | 8
1016190 | Story | UAT Support & Deployment Activities | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done |  | 2026-07-31 05:01 | 5 |  | 2026-07-29 | 2026-08-11 23:59 | True |  | 5 | 5
1016347 | Story | Dealer Weatlh Tool - Experience report logs | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-07-31 08:39 | 2 |  | 2026-07-29 | 2026-08-11 23:59 | True |  | 2 | 2
1018644 | Story | Fix Apex compilation errors & test-class failures across affected classes | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev; RELEVANT | 2026-08-04 14:00 | 3 |  | 2026-07-29 | 2026-08-11 23:59 | True |  | 3 | 3
1020579 | Bug | [Dynatrace App Synthetics] - Http monitor local outage for HTTP monitor JMA - Salesforce - IPs Check | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-08-06 13:50 | 2 |  | 2026-07-29 | 2026-08-11 23:59 | True |  | 2 | 2
Note on I11: Gina Pardini: 13 points not to be considered in metrics

## Sprint 17 Comit (hidden)
Commited
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation |  | Scope Creep Amount
838699 | Story | [Spike] End-to-End Payload Traceability and Attribute Validation for Salesforce-to-Synapse Account Canonicals Integration | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | carry-over 26.15; carry-over 26.16; Dev; RELEVANT | 2025-12-11 10:03 | 8 | 3 | 2026-08-12 | 2026-08-25 23:59 | False |  |  |  | 105
931743 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer Portal User |  | Sakshi Vazarde <conuumx@jmfamily.com> | In Progress | Admin; Blocked; carry-over 26.14; carry-over 26.15; carry-over 26.16; INFO | 2026-04-15 11:40 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
931776 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer User Info | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | In Progress | Admin; INFO | 2026-04-15 12:00 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
931789 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file SAP CPQ | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Progress | Admin; INFO | 2026-04-15 12:22 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False
946206 | Story | [Low] [Vulnerability Fix] Public static resources may expose data |  | felipe gonzalez <confjhw@jmfamily.com> | In Progress | carry-over 26.16; Dev; LOW | 2026-05-05 09:14 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
959000 | Story | [Low] [Vulnerability Fix] Third Party Applications are connected to an admin user | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | In Progress | Admin; carry-over 26.16; LOW | 2026-05-22 09:14 | 5 | 2 | 2026-08-12 | 2026-08-25 23:59 | False
965962 | Story | 08/19/2026 ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; ProdDeploy | 2026-06-02 16:19 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
984586 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file JMSC Forum | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Admin; carry-over 26.16; INFO | 2026-06-26 11:07 | 5 | 1 | 2026-08-12 | 2026-08-25 23:59 | False
989844 | Story | Create and Configure Salesforce Reference Sandbox for Integration Replication | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Ready for Sprint | Dev | 2026-07-02 08:33 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
991935 | Story | Commvault Phase 2 - Prepare Dedicated Salesforce Sandbox for Backup Validation | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | In Progress | Admin | 2026-07-07 10:35 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False
1001380 | Story | Fix API Error DSS - Authorize coupons in MTN Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Blocked; carry-over 26.15; Dev | 2026-07-14 13:35 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False
1001701 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.17 |  |  | Ready for Sprint | Admin; Dev | 2026-07-14 17:43 | 13 |  | 2026-08-12 | 2026-08-25 23:59 | False
1004134 | Story | [SPIKE] Enhancement: Determine Workday -> SalesConnect Integration to Capture Associate Data | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | Dev | 2026-07-15 15:15 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
1004762 | Story | [Spike][Critical] AI-11 - Assess OAuth Migration for Named Credentials | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | In Progress | Admin | 2026-07-16 10:02 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
1005763 | Story | [Spike] Investigate and resolve JMA_DEALER_ROLE__C canonical discrepancies between Salesforce and Synapse | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress | Dev; RELEVANT | 2026-07-17 09:26 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
1006172 | Story | IT Request: Forms Issue – Missing VF Box / Excel Data Not Populating | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | In Progress | Dev | 2026-07-17 15:30 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False
1011559 | Story | GitHub Release Enablement - Unit Test Remediation - Sales connect | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | carry-over 26.16; Dev | 2026-07-27 15:17 | 8 | 1 | 2026-08-12 | 2026-08-25 23:59 | False
1014332 | Story | [Security & Compliance] Destination System Assessment and Integration Design for Salesforce Security Log Backup Retention | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | In Progress | carry-over 26.16; Dev | 2026-07-29 11:52 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False
1018654 | Story | Reconcile test-failure count discrepancy between PROD and existing sandboxes | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | In Progress | Dev | 2026-08-04 14:03 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False
1018843 | Story | Create one sandbox per product team (target 15–20 total) - Sales Enablement | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Ready for Sprint | Admin | 2026-08-04 17:45 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | False
1019434 | Story | [Spike][Product Teams] Analyze Account type canonicals proposal and confirm readiness |  | Gina Pardini <conjsji@jmfamily.com> | In Progress | BA; carry-over 26.16 | 2026-08-05 12:58 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False
1020034 | Story | [Spike] Define SF Platform Sandbox Testing Strategy (Automation Coverage + Test Plan) |  | julieth barrera <conqhvn@jmfamily.com> | In Progress | Testing | 2026-08-05 23:03 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False
1020721 | Story | Cert Renewal for Mulesoft JWT jma-sf-mulesoft-jwt.jmfamily.com | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16 | 2026-08-06 16:54 | 2 | 1 | 2026-08-12 | 2026-08-25 23:59 | False
1022127 | Story | 08/12/2026 ¦ PROD Deployment ¦ SF Platform | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16; ProdDeploy | 2026-08-10 14:42 | 3 | 1 | 2026-08-12 | 2026-08-25 23:59 | False
1022744 | Story | DealerSource ¦ Confirmation Pop-up Does Not Display the Action Button Correctly in Coupon Authorization | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Progress | Dev | 2026-08-11 10:57 | 3 | 3 | 2026-08-12 | 2026-08-25 23:59 | False
1022796 | Story | UAT Support & Deployment Activities | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | In Progress | Admin | 2026-08-11 11:51 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False
1022839 | Story | CallMiner / Speech Analytics Integration – Sprint Support Activities | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | In Progress | CallMinner; Dev | 2026-08-11 12:08 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False
1023610 | Story | Create one sandbox per product team (target 15–20 total) - Digital Enablement | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Ready for Sprint | Admin | 2026-08-11 15:51 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | False
Actual
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points (Estimated) | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation | Commited | Scope Creep Amount | Done
989844 | Story | Create and Configure Salesforce Reference Sandbox for Integration Replication | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Ready for Sprint | carry-over 26.17; Dev | 2026-07-02 08:33 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False | 5
1011559 | Story | GitHub Release Enablement - Unit Test Remediation - Sales connect | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | carry-over 26.16; Dev | 2026-07-27 15:17 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1018654 | Story | Reconcile test-failure count discrepancy between PROD and existing sandboxes | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | In Progress | Dev | 2026-08-04 14:03 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1026458 | Story | INC0633707 – Investigate and Resolve Territory Account Ownership Reassignment Issue (PROD) | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev | 2026-08-14 13:03 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1026491 | Story | AccountTypeName Mapping – Current vs. Future State Analysis & Impact Validation Preparation | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev | 2026-08-14 13:46 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 5 | 5
1029130 | Story | Analysis: Online Claims needs access to Messaging Session record Transcripts | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev; NotImplement | 2026-08-20 06:09 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1028259 | Story | Dealer Source ¦ Modified Product Details are not getting updated through "Modify Product" button | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Removed |  | 2026-08-19 06:00 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 2 | 2
1031391 | Story | [SPIKE] Beqom: Investigate Null Account Number Values Impacting Dealer Data Processing | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Dev | 2026-08-24 15:34 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 5 | 5
1005763 | Story | [Spike] Investigate and resolve JMA_DEALER_ROLE__C canonical discrepancies between Salesforce and Synapse | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress | Dev; RELEVANT | 2026-07-17 09:26 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
984586 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file JMSC Forum | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Admin; carry-over 26.16; INFO | 2026-06-26 11:07 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
931743 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer Portal User | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Admin; Blocked; carry-over 26.14; carry-over 26.15; carry-over 26.16; INFO | 2026-04-15 11:40 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
838699 | Story | [Spike] End-to-End Payload Traceability and Attribute Validation for Salesforce-to-Synapse Account Canonicals Integration | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | carry-over 26.15; carry-over 26.16; Dev; RELEVANT | 2025-12-11 10:03 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1004134 | Story | [SPIKE] Enhancement: Determine Workday -> SalesConnect Integration to Capture Associate Data | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | Dev | 2026-07-15 15:15 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1019434 | Story | [Spike][Product Teams] Analyze Account type canonicals proposal and confirm readiness | Gina Pardini <conjsji@jmfamily.com> | Gina Pardini <conjsji@jmfamily.com> | Done | BA; carry-over 26.16 | 2026-08-05 12:58 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False | 0 |  | 0
1020721 | Story | Cert Renewal for Mulesoft JWT jma-sf-mulesoft-jwt.jmfamily.com | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16 | 2026-08-06 16:54 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | False | 2 |  | 2
1022127 | Story | 08/12/2026 ¦ PROD Deployment ¦ SF Platform | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16; ProdDeploy | 2026-08-10 14:42 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1023610 | Story | Create one sandbox per product team (target 15–20 total) - Digital Enablement | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-11 15:51 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | False | 2 |  | 2
1004762 | Story | [Spike][Critical] AI-11 - Assess OAuth Migration for Named Credentials | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Ready for Sprint | Admin; carry-over 26.17 | 2026-07-16 10:02 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False | 5
991935 | Story | Commvault Phase 2 - Prepare Dedicated Salesforce Sandbox for Backup Validation | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-07-07 10:35 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1031839 | Story | KB – Integration Certificate Renewal Process | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-25 09:37 | 1 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 1 | 1
1027171 | Story | INC0645500 Unable to Access Salesforce DSS/UAT via Mobile App - UAT | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-17 15:36 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1028617 | Bug | Salesforce CLI Error (AuthCodeExchangeError) | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-08-19 11:57 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
959000 | Story | [Low] [Vulnerability Fix] Third Party Applications are connected to an admin user | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | In Progress | Admin; carry-over 26.16; carry-over 26.17; LOW | 2026-05-22 09:14 | 5 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 5
965962 | Story | 08/19/2026 ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; ProdDeploy | 2026-06-02 16:19 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1018843 | Story | Create one sandbox per product team (target 15–20 total) - Sales Enablement | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Ready for Sprint | Admin; carry-over 26.17 | 2026-08-04 17:45 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 2
1006172 | Story | IT Request: Forms Issue – Missing VF Box / Excel Data Not Populating | julieth barrera <conqhvn@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | Done | Dev | 2026-07-17 15:30 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
931789 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file SAP CPQ | Mahika Agrawal <conjkak@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | In Progress | Admin; carry-over 26.17; INFO | 2026-04-15 12:22 | 8 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 8
1020034 | Story | [Spike] Define SF Platform Sandbox Testing Strategy (Automation Coverage + Test Plan) | julieth barrera <conqhvn@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | Done | Testing | 2026-08-05 23:03 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False | 0 |  | 0
1001380 | Story | Fix API Error DSS - Authorize coupons in MTN Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Blocked; carry-over 26.15; Dev | 2026-07-14 13:35 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1023907 | Bug | Dealer Source ¦ Authorized button's label gets disappear after providing RO number on Contract Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Progress | carry-over 26.17 | 2026-08-12 06:27 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | True |  | 2
1022744 | Story | DealerSource ¦ Confirmation Pop-up Does Not Display the Action Button Correctly in Coupon Authorization | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Dev | 2026-08-11 10:57 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1022796 | Story | UAT Support & Deployment Activities | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin | 2026-08-11 11:51 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
931776 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer User Info | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin; INFO | 2026-04-15 12:00 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1027252 | Story | INC0652217 Dynatrace HTTP Monitor Failure – JMA Salesforce IPs Check | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin | 2026-08-18 01:20 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 2 | 2
1031717 | Story | InfoSec Reporting Tracking in ADO - Part 1 | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Done | Dev | 2026-08-25 08:28 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
946206 | Story | [Low] [Vulnerability Fix] Public static resources may expose data | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Done | carry-over 26.16; Dev; LOW | 2026-05-05 09:14 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1022839 | Story | CallMiner / Speech Analytics Integration – Sprint Support Activities | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | In Progress | CallMinner; Dev | 2026-08-11 12:08 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1014332 | Story | [Security & Compliance] Destination System Assessment and Integration Design for Salesforce Security Log Backup Retention | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Done | carry-over 26.16; Dev | 2026-07-29 11:52 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1029039 | Story | [Elements Cloud] Enterprise Architecture Approval & Documentation | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:19 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1029053 | Story | GitHub Deployment Stabilization – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:28 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1029058 | Story | Sandbox Process Documentation & Training – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:37 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1029064 | Story | Cribl / Salesforce Data Retention Assessment – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:53 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1001701 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.17 |  |  | Done | Admin; Dev | 2026-07-14 17:43 |  |  | 2026-08-12 | 2026-08-25 23:59 | False | 13 |  | 0
[8 empty] | 162 | 18 |  |  |  |  | 44 | 135
144

## Sprint 17 Ago12-Ago25
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points (Estimated) | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation | Commited | Scope Creep Amount | Done
989844 | Story | Create and Configure Salesforce Reference Sandbox for Integration Replication | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Ready for Sprint | carry-over 26.17; Dev | 2026-07-02 08:33 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False | 5
1011559 | Story | GitHub Release Enablement - Unit Test Remediation - Sales connect | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | carry-over 26.16; Dev | 2026-07-27 15:17 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1018654 | Story | Reconcile test-failure count discrepancy between PROD and existing sandboxes | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | In Progress | Dev | 2026-08-04 14:03 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1026458 | Story | INC0633707 – Investigate and Resolve Territory Account Ownership Reassignment Issue (PROD) | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev | 2026-08-14 13:03 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1026491 | Story | AccountTypeName Mapping – Current vs. Future State Analysis & Impact Validation Preparation | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev | 2026-08-14 13:46 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 5 | 5
1029130 | Story | Analysis: Online Claims needs access to Messaging Session record Transcripts | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Done | Dev; NotImplement | 2026-08-20 06:09 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1028259 | Story | Dealer Source ¦ Modified Product Details are not getting updated through "Modify Product" button | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Removed |  | 2026-08-19 06:00 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 2 | 2
1031391 | Story | [SPIKE] Beqom: Investigate Null Account Number Values Impacting Dealer Data Processing | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Dev | 2026-08-24 15:34 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 5 | 5
1005763 | Story | [Spike] Investigate and resolve JMA_DEALER_ROLE__C canonical discrepancies between Salesforce and Synapse | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress | Dev; RELEVANT | 2026-07-17 09:26 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
984586 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file JMSC Forum | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Admin; carry-over 26.16; INFO | 2026-06-26 11:07 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
931743 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer Portal User | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Done | Admin; Blocked; carry-over 26.14; carry-over 26.15; carry-over 26.16; INFO | 2026-04-15 11:40 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
838699 | Story | [Spike] End-to-End Payload Traceability and Attribute Validation for Salesforce-to-Synapse Account Canonicals Integration | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | carry-over 26.15; carry-over 26.16; Dev; RELEVANT | 2025-12-11 10:03 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1004134 | Story | [SPIKE] Enhancement: Determine Workday -> SalesConnect Integration to Capture Associate Data | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | In Progress | Dev | 2026-07-15 15:15 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1019434 | Story | [Spike][Product Teams] Analyze Account type canonicals proposal and confirm readiness | Gina Pardini <conjsji@jmfamily.com> | Gina Pardini <conjsji@jmfamily.com> | Done | BA; carry-over 26.16 | 2026-08-05 12:58 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False | 0 |  | 0
1020721 | Story | Cert Renewal for Mulesoft JWT jma-sf-mulesoft-jwt.jmfamily.com | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16 | 2026-08-06 16:54 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | False | 2 |  | 2
1022127 | Story | 08/12/2026 ¦ PROD Deployment ¦ SF Platform | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin; carry-over 26.16; ProdDeploy | 2026-08-10 14:42 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1023610 | Story | Create one sandbox per product team (target 15–20 total) - Digital Enablement | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-11 15:51 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | False | 2 |  | 2
1004762 | Story | [Spike][Critical] AI-11 - Assess OAuth Migration for Named Credentials | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Ready for Sprint | Admin; carry-over 26.17 | 2026-07-16 10:02 | 5 | 5 | 2026-08-12 | 2026-08-25 23:59 | False | 5
991935 | Story | Commvault Phase 2 - Prepare Dedicated Salesforce Sandbox for Backup Validation | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-07-07 10:35 | 8 |  | 2026-08-12 | 2026-08-25 23:59 | False | 8 |  | 8
1031839 | Story | KB – Integration Certificate Renewal Process | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-25 09:37 | 1 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 1 | 1
1027171 | Story | INC0645500 Unable to Access Salesforce DSS/UAT via Mobile App - UAT | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done | Admin | 2026-08-17 15:36 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
1028617 | Bug | Salesforce CLI Error (AuthCodeExchangeError) | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Done |  | 2026-08-19 11:57 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
959000 | Story | [Low] [Vulnerability Fix] Third Party Applications are connected to an admin user | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | In Progress | Admin; carry-over 26.16; carry-over 26.17; LOW | 2026-05-22 09:14 | 5 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 5
965962 | Story | 08/19/2026 ¦ PROD Deployment ¦ SF Platform | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Done | Admin; ProdDeploy | 2026-06-02 16:19 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1018843 | Story | Create one sandbox per product team (target 15–20 total) - Sales Enablement | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Ready for Sprint | Admin; carry-over 26.17 | 2026-08-04 17:45 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 2
1006172 | Story | IT Request: Forms Issue – Missing VF Box / Excel Data Not Populating | julieth barrera <conqhvn@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | Done | Dev | 2026-07-17 15:30 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1020034 | Story | [Spike] Define SF Platform Sandbox Testing Strategy (Automation Coverage + Test Plan) | julieth barrera <conqhvn@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | Done | Testing | 2026-08-05 23:03 | 0 |  | 2026-08-12 | 2026-08-25 23:59 | False | 0 |  | 0
931789 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file SAP CPQ | Mahika Agrawal <conjkak@jmfamily.com> | julieth barrera <conqhvn@jmfamily.com> | In Progress | Admin; carry-over 26.17; INFO | 2026-04-15 12:22 | 8 | 2 | 2026-08-12 | 2026-08-25 23:59 | False | 8
1001380 | Story | Fix API Error DSS - Authorize coupons in MTN Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Blocked; carry-over 26.15; Dev | 2026-07-14 13:35 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1023907 | Bug | Dealer Source ¦ Authorized button's label gets disappear after providing RO number on Contract Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Progress | carry-over 26.17 | 2026-08-12 06:27 | 2 | 2 | 2026-08-12 | 2026-08-25 23:59 | True |  | 2
1022744 | Story | DealerSource ¦ Confirmation Pop-up Does Not Display the Action Button Correctly in Coupon Authorization | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Done | Dev | 2026-08-11 10:57 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | False | 3 |  | 3
1022796 | Story | UAT Support & Deployment Activities | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin | 2026-08-11 11:51 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
931776 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file Dealer User Info | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin; INFO | 2026-04-15 12:00 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1027252 | Story | INC0652217 Dynatrace HTTP Monitor Failure – JMA Salesforce IPs Check | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Done | Admin | 2026-08-18 01:20 | 2 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 2 | 2
1031717 | Story | InfoSec Reporting Tracking in ADO - Part 1 | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Done | Dev | 2026-08-25 08:28 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True |  | 3 | 3
946206 | Story | [Low] [Vulnerability Fix] Public static resources may expose data | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Done | carry-over 26.16; Dev; LOW | 2026-05-05 09:14 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1022839 | Story | CallMiner / Speech Analytics Integration – Sprint Support Activities | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | In Progress | CallMinner; Dev | 2026-08-11 12:08 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1014332 | Story | [Security & Compliance] Destination System Assessment and Integration Design for Salesforce Security Log Backup Retention | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Done | carry-over 26.16; Dev | 2026-07-29 11:52 | 5 |  | 2026-08-12 | 2026-08-25 23:59 | False | 5 |  | 5
1029039 | Story | [Elements Cloud] Enterprise Architecture Approval & Documentation | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:19 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True | 3 |  | 3
1029053 | Story | GitHub Deployment Stabilization – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:28 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True | 3 |  | 3
1029058 | Story | Sandbox Process Documentation & Training – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:37 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True | 3 |  | 3
1029064 | Story | Cribl / Salesforce Data Retention Assessment – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Done | Admin | 2026-08-19 16:53 | 3 |  | 2026-08-12 | 2026-08-25 23:59 | True | 3 |  | 3
1001701 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.17 |  |  | Done | Admin; Dev | 2026-07-14 17:43 |  |  | 2026-08-12 | 2026-08-25 23:59 | False | 13 |  | 0

## Sprint 18 Ago26-Sep08 (commit)
ID | Work Item Type | Title | Developer | Assigned To | State | Tags | Created Date | Story Points | Carry Over | Sprint Start Date | Sprint End Date | Scope Creep Validation | Scope Creep Amount | Commited
820264 | Story | General Analysis: Winter 2027 Salesforce release | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Committed to Sprint | Dev | 2025-11-11 12:16 | 5 |  | 2026-08-26 | 2026-09-08 23:59
937443 | Task | 8. Execute pilot in at least two developer sandboxes | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | In Backlog |  | 2026-04-22 10:25 |  |  | 2026-08-26 | 2026-09-08 23:59
937444 | Task | 9. Stakeholder review and sign-off | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | In Backlog |  | 2026-04-22 10:26 |  |  | 2026-08-26 | 2026-09-08 23:59
989844 | Story | Create and Configure Salesforce Reference Sandbox for Integration Replication | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Committed to Sprint | carry-over 26.17; Dev | 2026-07-02 08:33 | 5 | 5 | 2026-08-26 | 2026-09-08 23:59
1028882 | Story | Analysis Sanboxes: Winter 2027 Salesforce release | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Committed to Sprint | Dev | 2026-08-19 15:17 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1031380 | Story | AccountTypeName Mapping – Current vs. Future State Analysis & Impact Validation Preparation | Apala Sen <conjzwj@jmfamily.com> | Apala Sen <conjzwj@jmfamily.com> | Committed to Sprint | Dev; RELEVANT | 2026-08-24 15:19 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1029141 | Task | Trace and Validate Salesforce-to-Synapse Role Data | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress |  | 2026-08-20 07:09 |  |  | 2026-08-26 | 2026-09-08 23:59
1029142 | Task | Document Root Cause and Recommend Remediation | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress |  | 2026-08-20 07:10 |  |  | 2026-08-26 | 2026-09-08 23:59
1008149 | Story | Guided Tour Tooltip Appears Misaligned During New User Onboarding in Production | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Committed to Sprint | Dev; RELEVANT | 2026-07-22 09:01 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1021805 | Story | [Destructive Change] Removal/Disable of JMSC Forum Connected App | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Removed | Dev | 2026-08-10 09:35 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1004745 | Story | [Spike][High] AI-02 - Assess Connected App IP Restriction Enforcement | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Committed to Sprint | Dev | 2026-07-16 09:52 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1005763 | Story | [Spike] Investigate and resolve JMA_DEALER_ROLE__C canonical discrepancies between Salesforce and Synapse | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | In Progress | carry-over 26.17; Dev; RELEVANT | 2026-07-17 09:26 | 5 | 1 | 2026-08-26 | 2026-09-08 23:59
1005768 | Story | ServiceProviderRelationshipEvent records with null dealerFWSNumber | Ataul Khalique <coniubj@jmfamily.com> | Ataul Khalique <coniubj@jmfamily.com> | Committed to Sprint | Dev; RELEVANT | 2026-07-17 09:34 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1004702 | Story | [Spike][Critical] IAC-93 - Assess Requiring POST for Cross-Domain Sessions | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Committed to Sprint | Dev | 2026-07-16 09:34 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1004737 | Story | [Spike][Critical] IAC-116 - Assess COEP Enablement | Carlos Juarez <conkqse@jmfamily.com> | Carlos Juarez <conkqse@jmfamily.com> | Committed to Sprint | Dev | 2026-07-16 09:48 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1031697 | Task | [DS] [AUG 26 - SEP 01] Regression Testing |  | felipe gonzalez <confjhw@jmfamily.com> | In Backlog | SP18 | 2026-08-25 08:21 |  |  | 2026-08-26 | 2026-09-08 23:59
1031698 | Task | [SC] [AUG 26 - SEP 01] Regression Testing |  | felipe gonzalez <confjhw@jmfamily.com> | In Backlog | SP18 | 2026-08-25 08:21 |  |  | 2026-08-26 | 2026-09-08 23:59
1031072 | Story | Q3 ¦ 2026 Recurrent Task: Regression testing |  | felipe gonzalez <confjhw@jmfamily.com> | Committed to Sprint | Testing | 2026-08-24 11:14 | 0 |  | 2026-08-26 | 2026-09-08 23:59
1031078 | Task | [RRH] [AUG 26 - SEP 01] Regression Testing |  | felipe gonzalez <confjhw@jmfamily.com> | In Backlog | SP18 | 2026-08-24 11:17 |  |  | 2026-08-26 | 2026-09-08 23:59
1032444 | Task | Testing - IT Request: Forms Issue – Missing VF Box / Excel Data Not Populating |  | felipe gonzalez <confjhw@jmfamily.com> | In Progress |  | 2026-08-25 17:04 |  |  | 2026-08-26 | 2026-09-08 23:59
1031360 | Story | 09/02/2026 ¦ PROD Deployment ¦ SF Platform | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Committed to Sprint | Admin; ProdDeploy | 2026-08-24 15:03 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1032423 | Story | [Recurrent][Sprint 26.18] Salesforce Deployment Support (UAT & PROD) | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 16:00 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1004762 | Story | [Spike][Critical] AI-11 - Assess OAuth Migration for Named Credentials | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Committed to Sprint | Admin; carry-over 26.17 | 2026-07-16 10:02 | 5 | 5 | 2026-08-26 | 2026-09-08 23:59
1007845 | Story | [Spike] Secure Endpoint Name Credentials Status in Production | Ignacio Toledo <conmcxf@jmfamily.com> | Ignacio Toledo <conmcxf@jmfamily.com> | Removed |  | 2026-07-21 18:58 |  |  | 2026-08-26 | 2026-09-08 23:59
1022335 | Task | Task 1: Sales Enablement | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | In Backlog |  | 2026-08-10 17:12 |  |  | 2026-08-26 | 2026-09-08 23:59
1018843 | Story | Create one sandbox per product team (target 15–20 total) - Sales Enablement | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Committed to Sprint | Admin; carry-over 26.17 | 2026-08-04 17:45 | 2 | 2 | 2026-08-26 | 2026-09-08 23:59
1004693 | Story | [Spike][Critical] IAC-94 - Assess Enforcing Login IP Ranges on Every Request | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Committed to Sprint | Admin | 2026-07-16 09:29 | 5 |  | 2026-08-26 | 2026-09-08 23:59
959000 | Story | [Low] [Vulnerability Fix] Third Party Applications are connected to an admin user | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | In Progress | Admin; carry-over 26.16; carry-over 26.17; LOW | 2026-05-22 09:14 | 5 | 2 | 2026-08-26 | 2026-09-08 23:59
1032282 | Story | Update STAGE Salesforce Account Records to Include Integration Fields for Testing | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 14:49 | 1 |  | 2026-08-26 | 2026-09-08 23:59
1032419 | Story | [Recurrent][Sprint 26.18] Salesforce Deployment Support (UAT & PROD) | Jacobo Salazar <contytk@jmfamily.com> | Jacobo Salazar <contytk@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 15:55 | 2 |  | 2026-08-26 | 2026-09-08 23:59
931789 | Story | [Info] [Vulnerability Fix] Connected app scopes for this org in file SAP CPQ |  | julieth barrera <conqhvn@jmfamily.com> | In Progress | Admin; carry-over 26.17; INFO | 2026-04-15 12:22 | 8 | 2 | 2026-08-26 | 2026-09-08 23:59
1005361 | Story | [Spike][High] IAC-07 - Assess MFA Coverage for API Access | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Committed to Sprint | Admin | 2026-07-16 16:40 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1004747 | Story | [Spike] [Critical] IAC-86 - Assess Session Locking to Originating IP | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Committed to Sprint | Admin | 2026-07-16 09:54 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1022339 | Task | Task 4: BT Team | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Backlog |  | 2026-08-10 17:14 |  |  | 2026-08-26 | 2026-09-08 23:59
1023614 | Story | Create one sandbox per product team (target 15–20 total) - BT Team | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Committed to Sprint | Admin | 2026-08-11 15:52 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1023907 | Bug | Dealer Source ¦ Authorized button's label gets disappear after providing RO number on Contract Services | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | In Progress | carry-over 26.17 | 2026-08-12 06:27 | 2 | 2 | 2026-08-26 | 2026-09-08 23:59
1032422 | Story | [Recurrent][Sprint 26.18] Salesforce Deployment Support (UAT & PROD) | Mahika Agrawal <conjkak@jmfamily.com> | Mahika Agrawal <conjkak@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 15:59 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1032424 | Story | [Recurrent][Sprint 26.18] Salesforce Deployment Support (UAT & PROD) | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 16:01 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1031751 | Story | [Vulnerability Fix] Remove OAuth Scopes – Dealer User Info | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Committed to Sprint | Admin; INFO | 2026-08-25 09:01 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1023612 | Story | Create one sandbox per product team (target 15–20 total) - OCS Claims | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Committed to Sprint | Admin | 2026-08-11 15:52 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1022338 | Task | Task 3: OCS Claims | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | In Backlog |  | 2026-08-10 17:14 |  |  | 2026-08-26 | 2026-09-08 23:59
1004670 | Story | [Spike][Critical] IAC-147 - Assess Login IP Range Enforcement Strategy | Manish Raj <conuazh@jmfamily.com> | Manish Raj <conuazh@jmfamily.com> | Committed to Sprint | Admin | 2026-07-16 09:18 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1006172 | Story | IT Request: Forms Issue – Missing VF Box / Excel Data Not Populating | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Done | carry-over 26.17; Dev | 2026-07-17 15:30 | 3 | 2 | 2026-08-26 | 2026-09-08 23:59
1029951 | Story | Recurring - Sprint 26.18: SNOW Incident Triage & Management | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Committed to Sprint | Dev | 2026-08-20 16:54 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1029952 | Story | Recurring - Sprint 26.18: SNOW Request & Task Management | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Committed to Sprint | Dev | 2026-08-20 16:55 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1029953 | Story | Recurring - Sprint 26.18: SNOW Dashboard Monitoring & Operational Reporting | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | Committed to Sprint | Dev | 2026-08-20 16:56 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1031720 | Story | InfoSec Reporting Tracking in ADO - Part 2 | Santiago Epalza <conftst@jmfamily.com> | Santiago Epalza <conftst@jmfamily.com> | In Progress | Dev | 2026-08-25 08:31 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1004742 | Story | [Spike][Critical] IAC-115 - Assess COOP Enablement | Sebastian Perez <conlbqr@jmfamily.com> | Sebastian Perez <conlbqr@jmfamily.com> | Committed to Sprint | Dev | 2026-07-16 09:50 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1025920 | Story | [Spike] Analyze Secret Exposure Vulnerability – solutions-salesforceproxy-shared |  | Sujit Sarkar <coniunq@jmfamily.com> | Ready for Sprint | Admin | 2026-08-13 17:11 |  |  | 2026-08-26 | 2026-09-08 23:59
1001680 | Story | Speech Analytics Integration - Establish an integration user - PROD | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Committed to Sprint | Dev; RELEVANT | 2026-07-14 17:01 | 2 |  | 2026-08-26 | 2026-09-08 23:59
1001681 | Story | Speech Analytics Integration - Create and Configure External Client App - PROD | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Committed to Sprint | Dev; RELEVANT | 2026-07-14 17:01 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1031804 | Story | [Spike] Salesforce Event Retention – External Storage Integration Design | Tomas Olivera <conkgku@jmfamily.com> | Tomas Olivera <conkgku@jmfamily.com> | Committed to Sprint | Dev | 2026-08-25 09:13 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1032434 | Story | Cribl / Salesforce Data Retention Assessment – Part 2 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 16:29 | 3 |  | 2026-08-26 | 2026-09-08 23:59
1032438 | Story | [Elements Cloud] Enterprise Architecture Approval Follow-up | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Committed to Sprint | Admin | 2026-08-25 16:50 | 1 |  | 2026-08-26 | 2026-09-08 23:59
1029058 | Story | Sandbox Process Documentation & Training – Part 1 | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Committed to Sprint | Admin; carry-over 26.17 | 2026-08-19 16:37 | 3 | 3 | 2026-08-26 | 2026-09-08 23:59
1025918 | Story | [Spike] Analyze GitHub CI/CD Workflow Permissions Vulnerabilities – sf-platform | Victor Cabrera <congize@jmfamily.com> | Victor Cabrera <congize@jmfamily.com> | Committed to Sprint | Admin | 2026-08-13 16:57 | 5 |  | 2026-08-26 | 2026-09-08 23:59
1031359 | Story | Recurring: Salesforce KLO/Administration and Support ticket's Triage - Sprint 26.18 |  |  | Committed to Sprint | Admin; Dev | 2026-08-24 15:02 | 13 |  | 2026-08-26 | 2026-09-08 23:59